## Slide 1: Thèse – S09
Christian Wilkinson

## Slide 2: TABLE OF CONTENTS Summary of objectives 01 03 02 Ariel School summary
Objectives

## Slide 3: Summary of objectives 01

## Slide 4: Summary of objectives
ARIEL school + summary of lessons + work completed (~2 weeks) - Completed
Continue learning EOS and interior physics (~2 weeks) - Late
Have global understanding of Exorem codes (~1 month) – Continuing (J-K curves)
Have global understanding of Exoris codes (~1 month) – Not started
Start to use Exorem + Exoris together (~1 month) – Not started
Start to explore coding P.Tremblin’s fingering convection (ATMOS) (~1 month >) - Not started

## Slide 5: Ariel School summary 02

## Slide 6: Ariel School summary
Plantary atmospheres – Thermodynamics
  Equilibrium/Disequilibrium/Photo Chemistry
Atmosphere dynamics
  Circulation cells, adiabatic and non adiabatic gradients
Links between solar system and exoplanets
  Escape models, Cloud microphysics, Radiatif transfer
Imaging – Hubble
Intro to Baysean statistics
Turorials
  GCM, chemistry models, retrieval (Taurex)
Practice sessions
  Building transmission spectrums
  Retrieving planet with spectrums

## Slide 7: Further work, conclusion, discussion 03

## Slide 8: Further work, conclusion, discussion
Continue learning EOS and interior physics (~1 week)
Have global understanding of Exorem codes (~2 weeks)
Have global understanding of Exoris codes (~2 weeks) - (Friday meeting with S. Mazevet)
Start to use Exorem + Exoris together (2 months)
Start to explore coding P.Tremblin’s fingering convection (ATMOS) (~1 month >)